## Project_Schedule
WBS Task ID | Task Description | Assigned Lead | Start Date | Days Allocated | Completion % | Status
1.1 | Architecture Audit & Scope Definition | Raymond Zhao | 2026-11-01 | 10 | 1 | Completed
1.2 | Database Schema & API Contract Design | Alex Mercer | 2026-11-12 | 15 | 0.85 | In Progress
2.1 | Frontend UI Design System & Components | Elena Rostova | 2026-11-20 | 20 | 0.6 | In Progress
2.2 | Core Microservices Backend Implementation | Alex Mercer | 2026-12-01 | 25 | 0.3 | In Progress
3.1 | Integration Testing & Security Penetration | Sarah Miller | 2026-12-20 | 12 | 0 | Scheduled
3.2 | User Acceptance Testing (UAT) | David Sterling | 2027-01-05 | 14 | 0 | Scheduled
4.1 | Production Deployment & Go-Live | Raymond Zhao | 2027-01-20 | 5 | 0 | Scheduled